## Slide 1: MONITORING OF FIRST DRIVE OF MISSION INDRADHANUSH AT DEOGHAR DISTRICT,JHARKHAND (06/04/2015-12/05/2015) By- Hansa Lala, PG/13/024 Organization-NHSRC, New Delhi

## Slide 2: MISSION INDRADHANUSH
Since 2009-2013,there has been increase in immunization coverage from 61% to 65%,annual increase of merely 1%
Launched in December 2014 by Ministry of Health and Family Welfare to maximize immunization
Focus- To improve immunization from 65% to 90% in next five years
Will be in catch up mode
Four planned sessions, 7 days a month (1week)
Included unreachable areas to strengthen Universal Immunization Programme

## Slide 3: MISSION INDRADHANUSH

## Slide 4: STATUS OF IMMUNIZATION IN JHARKHAND
Chart: Immunization performance in Jharkhand
| NFHS(2005-2006) | DLHS(2007-2008) | CES(2009) | AHS(2012-13)
 | 34 | 54 | 60 | 69

## Slide 5: DISTRICTS SELECTED FOR MISSION INDRADHANUSH-JHARKHAND
Chart: 
| Jharkhand | Deoghar | Dhanbad | Giridih | Godda | Pakur | Sahibganj
AHS(2010-11) | 63.7 | 40.6 | 60.2 | 28 | 44.1 | 45.7 | 54.9
AHS(2011-12) | 69.1 | 48.6 | 67.2 | 43 | 54 | 54.9 | 60.7
AHS(2012-13) | 69.9 | 56.3 | 69.3 | 46.5 | 55.9 | 47.6 | 57.9

## Slide 6: STUDY-METHODOLOGY
Objective of study
  General Objective: To understand overall input, processes and functioning of Mission
  Indradhanush in Deoghar District of Jharkhand
Specific Objective-
  To understand pre-implementation activities of Mission Indradhanush at district and block level
  To observe and examine the actual implementation of programme at the village and sub-centre level
Type of Study-Descriptive
Tool used-
  District assessment Checklist (Ministry of Health and Family Welfare)
  Block assessment Checklist (Ministry of Health and Family Welfare)
  Session site monitoring

## Slide 7: STUDY
DISTRICT MONITORED
Deoghar District, Jharkhand
BLOCKS COVERED
Sarad
Sarwan
Jasidih
Devipur
SESSION SITES MONITORED(SUB-CENTRE)
Kachuabagh (Block Sarad)
Kapsa2(Block Sarad)
Nandan Pahad 2(Urban Deoghar)

## Slide 8: FINDINGS
Pre- implementation activities
STAKEHOLDERS | ACTIVITIES
Health Department, Health and Family welfare, Deoghar, Jharkhand | District Task Force Meeting, Training of Medical Officer In-Charge for MI, Financial assistance to block level, Communication planning(Information Education Communication),Monitoring the drive through District and block Observer
World Health Organization, India | Technical Support in planning, of Microplans, Monitoring the drive and feedback
UNICEF and CINI(Child in need Institute) | Communication Planning at District and block level(Nukkad Natak etc) and cold chain maintainance

## Slide 9: FINDINGS-DISTRICT LEVEL
DTFI Meeting
Financial norms for MI
Status of District Task Force Meeting | Partners(Stakeholders) invited | Partners joined for the meeting | Partners who did not attended the meeting
Held, twice (19/3/2015) and 4/4/2015,chaired by District Magistrate | WHO, UNICEF, Rotary, Core RMNCH+A Partners, IMA,IAP, Others | WHO,UNICEF, RMNCH+A Partners | Rotary, Indian Medical Association, Indian Association, of Pediatricians Others
Does district have clarity on financial norms? Is District mmunization Officer(DIO) aware of flexibility under Mission Indradhanush? | Yes
Does DIO have clarity on funding of Information Education Communication? | No

## Slide 10: FINDINGS-DISTRICT LEVEL
Communication Planning
Trainings conducted- Medical Officers, NHM Finance Mangers, Vaccine Cold Chain Managers
No media workshop was conducted
Has district prepared a communication plan | Modes of IEC used | What all not done
Yes(But not robust planning) | Pamphlets, Posters, Newspaper, Flex board | No social mobilization campaign No pre monitoring of communication activities No advocacy engagements No dedicated plan for unreached areas, high priority areas

## Slide 11: CONTINUED…
Monitoring of Drive
Four district level observers four were allocated
One WHO monitoring Officer for entire Mission Indradhanush
One state monitor was allocated from Ranchi Office
Block development Officers were allocated to monitor the drive for respective blocks
One National monitor for entire District
Review meeting
District level- daily evening meeting headed by Civil surgeon, WHO , National and district monitors
Block level-Daily review meeting by Block development officer, Medical Officer In-Charge

## Slide 12: BLOCK LEVEL-PRE IMPLEMENTATION ACTIVITIES
Mapping out of head counts was done majorly by ANM, reported to Block MOIC
Rosters for ANM were prepared in advance by MOIC and Block Manager for allotment of their respective session site, date and activities during seven days
Microplan was made by the blocks and was sent to District RCHO Officer
Communication planning
No Block level Planning for Communication strategy for local villages, hard reach areas
Information Education Communication(IEC) material used-From District level
Trainings and workshops
Conducted for ANM, ASHA (Sahiya) in two rounds by MOIC
No training for Helpers and link workers

## Slide 13: IMPLEMENATION PHASE-SESSION SITE
AT DISTRICT LEVEL
Inauguration was done on 7/04/2015 by District Collector, Deoghar at District Hospital
Microplan present from all Blocks
Daily evening review meeting at District level conducted, headed by Civil Surgeon.
Other members present-WHO Monitor, National monitor, District Observer with Block reviews and data
BLOCK LEVEL- Kapsa 2 (Block Sarad)
IEC materials pasted and displayed in around session site.
ANM and Sahiya both were present
Sahiya was trained but not aware of headcount and checklist
ANM conducted the head count
Microplan and due list present
ASHA was not much aware about the entire programme

## Slide 14: IMPLEMENTATION AT BLOCK LEVEL
Kachuabagh Session site (Block Sarad)
IEC Material was received by ASHA/ANM one day before the drive to start
IEC was not at all displayed and pasted on the session site
No local communication activities other then IEC were conducted
No ASHA (Sahiya) was allotted in the session site. Helper for ANM conducted head count and other activities
High refusal rate
Due list was not present, head count and tally sheet was present

## Slide 15: CONTINUED
Nandan Pahad (Urban area- Deoghar)
Headcount, due list, microplan ,tally sheet present and verified
IEC material were displayed properly
ANM present, posted from other block but trained for MI.
Two Sahiya’s were allocated for this session site, both trained for MI.
A vaccine vial was found without expiry and opening date.

## Slide 16: OTHER FINDINGS
Lack of Human Resource at Block level
CHC with high work load and one MOIC ,management is difficult
Lack of transportation facilities for ANM,ASHA to hard reach areas, therefore late session start
Block MOIC’s not aware of letter for ANM from MohFW
IEC material were despatched one day before the drive at the Block level
No Block level communication planning was made
Lack of motivation from ASHA ,therefore high refusal rate in some areas

## Slide 17: RECOMMENDATIONS
Involvement of participation of IAP, IMA, Rotary members in DTFI meeting
Submission of microplan at least 15 days before the drive
Transportation facility for ASHA/ANM should be looked upon
Communication Planning at Block level should be focused with more involvement of NGO
Special focus of communication planning for Village and sub-centre level
Emphasis on training of Block Managers for MI
More addressing of motivational factors through ASHA in high refusal rate
Training of ASHA in preparation of head count and due list should be more emphasized with practical training

## Slide 18: Thank you By: Hansa Lala PG/13/024